Examples of UNDAFs that reflect Results Based Management

Papua New Guinea (2008-2012)

The UN Country Programme (UNCP) in Papua New Guinea is a `self-starter` for the Delivering as One (DaO) approach. It contains many key elements that are important for the practice of results-based management (RBM). These elements are relevant to most UNDAF countries:

- The UNCP applies lessons from the evaluation of the previous UNDAF cycle (2003-2007), with a focus on performance management:

- More consistent linkages between UNCP and agency Country Programmes and greater flexibility to adjust resources and results;

- More systematic and effective monitoring, through regular progress reports, coupled with strengthening of Steering Committees and tripartite review systems, to address performance and key issues;

- Continuous and effective functioning of theme groups for monitoring results with designation of Team Leaders for each thematic area;

- More systematic and long -term partnerships with donors through the use of the programme approach and outcome area results matrixes and annual work plans.

- A single Results and Monitoring and Evaluation Matrix is used to combine the Results Matrix and the Monitoring and Evaluation Plan. This ensures that outcomes and outputs are measurable, and clearly linked with appropriate indicators, sources of verification, and risks and assumptions.

- Flexibility: The UNCP is a “rolling” framework, to be reviewed and validated on an annual basis when preparing annual work plans. UNCP outcomes, outputs and agency support will be adjusted in the light of changing national and UN priorities, and available resources

- Alignment: The UNCP Results and Monitoring and Evaluation Frameworks is aligned with the National policy and planning framework and results information is designed to feed into the Government`s Performance Management Framework. The UNCP includes results and key activities to support Government efforts to strengthen national monitoring and statistical services, and avoiding the creation of a parallel M&E systems.

- Building on UNCT comparative advantages: The narrative for each of the major results sections provides a detailed description of UNCT comparative advantages for action, and ties these to the results expected.

- Enhanced monitoring and evaluation mechanisms and procedures are established, and these are presented in a clear, understandable table of  coordination mechanisms for monitoring and management (p.32-33). The overall focus is directed towards managing for UNCP outcomes:

- Quarterly reporting on progress towards outcomes, complemented by an annual review.

- A Steering Committee for each outcome with Government, UN, other partner, and donor representatives.

- The primary tool for Outcome monitoring is the Annual Work Plans. Responsibility for monitoring lies with the Task Team Leader who will receive guidance from the UNCT and technical support from the UN Coordination Office’s M&E specialist.

- The UNCT will monitor progress towards the planned outcomes through reviews of bi -monthly progress reports from the Team Leaders in relation to the progress achieved against the Annual Work Plan.

- Quality of results

- The UNCP results framework shows consistent use of change language in the formulation of results

- Overall, the phrasing of results is relatively simple and straight-forward, such that a non-specialist can understand the purpose

- There is intuitive causality between most of the results levels

- Most indicators and means of verification are logical

- Much attention has been paid to the identification of risks and assumptions that underlie the programme design;

- Details of implementing partners are specific, as are resource estimates.

Namibia (2006-2010)

- The UNDAF argues for, and presents, a results-based management framework focused on accountability and transparency through effective monitoring and evaluation

- It builds on lessons from the previous UNDAF cycle:

- More effective engagement with the Namibian Government and stakeholders through multisectoral committees and working groups;

- More joint efforts and opportunities for planning and review of UN assistance activities, especially for common counterpart ministries

- Avoid the creation of parallel or additional structures.

- The UNDAF contains strong statements about the importance of the results matrix and M&E plan as the ``basic tools`` for monitoring performance and mobilising resources

- The UNDAF lays out a clear structure for UNDAF monitoring and reporting, with a single UNDAF working group for each outcome, linked to specific government teams and mechanisms, for monitoring and reporting

- The UNDAF includes results to strengthen the capacity of the Government to monitor progress towards development goals, by harmonizing data collection systems, providing support for databases and analysis tools, and for improving dissemination of findings.

- The UNDAF results matrix and M&E plan were developed with a high level of stakeholder participation. A Core Group, was co-chaired by the Under-Secretary of Health and Social Services and the Director of Development Cooperation. Three Technical Working Groups were formed, with stakeholders from government, civil society and the relevant UN agencies (resident and non-resident).

- Quality of results

- There is consistency between the results in the matrix and in the M&E Plan

- Results are formulated with change language, and the language is easily understandable and free of jargon

- Causality between the results levels is intuitive

- There are a reasonable number of indicators, they are appropriate to the results, and great care has been taken to complete information about baselines and targets

- The sources of verification are complete

- Careful attention has been paid to the identification of risks and assumptions;

- Details of implementing partners are specific, as are resource estimates.

Nepal (2008-2010)

- Priority setting for the Nepal UNDAF is linked concretely to the findings in the CCA, and is based on several strategic criteria, including: contribution to sustainable peace, and reaching socially excluded and economically marginalized groups.

- The narrative (section 2.6) provides a detailed description of key risks which may hinder implementation, and these are linked to specific outcomes in the results matrix.

- The UNDAF lays out a simple management structure and coordination mechanisms to manage and monitor UNDAF performance. The emphasis is placed on creating a management environment for meaningful review, and dialogue with stakeholders

- UNDAF working groups are tasked to monitor UNDAF performance and report to the UNCT with recommendations for adjustments to results and resources

- Regular donor coordination meetings are planned to ensure dialogue with partners, identify areas for joint programming, and avoid duplication.

- A UNDAF Monitoring and Evaluation group provides a quality check throughout the process, but particularly in the application and updating of the M&E plan

- Indicators are used from Government monitoring systems (the Poverty Monitoring and Analysis System, the Health Management Information System and the Education Management Information System)

- Quality of results

- There is consistency between the results in the matrix and in the M&E Plan

- Results are formulated with change language. Some results are too wordy, but the language and concepts are understandable and mostly free of jargon

- Causality between the results levels is logical

- Indicators are kept at a modest number and are appropriate to the results

- Baseline information is included where available, and flagged for attention where not

- The sources of verification are complete and intuitive

- Risks and Assumptions are identified at the outcomes level, where they are most critical;

- Details of implementing partners are specific, as are resource estimates.

This combined table is now consistent with the structure of the UNDAF Results Matrix in the 2010 UNDAF Guidelines.