## Slide 1: The UNDAF: Linking Analysis with Results Annex of additional slides Session 6
Notes: Expected Results
Participants have a common understanding of RBM, and can explain how a HRBA strengthens the formulation of results and indicators
Participants have practiced the formulation of outcomes, outputs, and indicators, on the basis of a human rights-based analysis
Participants have a better sense of the struggle that many UNCTs go through as they attempt to formulate SMART results in the inter-agency setting

## Slide 2: Accountability for Results
For the UNDAF, mutual accountability means the respective accountability of parties working together towards shared outcomes
UNCTs are accountable for outcomes, they are not wholly responsible for their achievement.
Notes: HIDDEN SLIDE
RBM Handbook, p. 8-10 THIS HANDBOOK IS STILL IN DRAFT VERSION AND NOT YET AVAILABLE FOR DISTRIBUTION – THIS NOTE IS FOR FACILITATORS REFERENCE ONLY
Accountability for Results
The concept of ‗mutual accountability‘ has become established as a consideration of development and aid effectiveness, although questions remain on its actual implications. For the purpose of the UNDAF, mutual accountability is interpreted to mean the respective accountability of parties working together towards shared outcomes. This notion of respective accountability‘ reflects the fact that accountability is not fungible and must, in the final analysis, be attached to a specific actor. Many stakeholders contribute to UNDAF outcomes and each is accountable for its contribution.
UN funds, programmes and specialized agencies as members of the UNCT collaborate with national counterparts to determine the outcomes of the UN support in a particular country. The outcomes of UN support are framed in the United Nations Development Assistance Framework (UNDAF) or other agreed common document and always derive from the country‘s national development objectives.
UNCT members are accountable to partner governments for their overall contribution to national development objectives through their contribution to the achievement of specific UNDAF-level outcomes
Put another way…UNCTs are accountable for outcomes, they are not wholly responsible for their achievement.
2

## Slide 3: Outcomes: Definition & key features
Changes in institutional performance or behaviours
Strategic contribution to the country priorities/MDGs
Number of outcomes depends on challenges and UNCT comparative advantages
Collective priorities (but do not require contributions from every agency)
Produced by the combined effects of the contributing outputs
Reflect a choice about strategy or policy
Notes: HIDDEN SLIDE
RBM Handbook, p.19 THIS HANDBOOK IS STILL IN DRAFT VERSION AND NOT YET AVAILABLE FOR DISTRIBUTION – THIS NOTE IS FOR FACILITATORS REFERENCE ONLY
Outcomes describe the intended changes in development conditions resulting from UNCT cooperation. They relate to changes in institutional performance or behaviour among individuals or groups as viewed through a human rights-based approach lens. Achievement of outcomes depends critically on the commitment and actions of stakeholders, as well as on results to be achieved by government and partners outside the UNDAF.
UNDAF outcomes are the collective strategic results for UN system cooperation at the country level, intended to support achievement of national priorities. UNDAF outcomes should be specific, strategic and clearly contribute to national priorities, and must also be linked to and supported by programme or project outputs. Outputs should be linked to those accountable for them and the results chain should have a much stronger internal logic. Indicators should also help to measure UNDAF outcomes on a regular basis so that decision-making is informed by relevant data.
Indicators are necessary to measure achievement of the outcomes and outputs. More detailed guidance on how to develop outcome and output statements is available in the technical briefs for outcomes and outputs.
3

## Slide 4: Outputs: Definition & key features
Concrete, deliverables
Operational changes: new skills or abilities, the availability of new products and services
Must be achieved within the programme period
Managers have a high degree of control
   If the result is mostly beyond the control or influence of the programme or project, it cannot be an output
Failure to deliver is failure of the programme or project
Unless under a joint programme, outputs are NOT collective results
Notes: 4
HIDDEN SLIDE
RBM Handbook, p.19 THIS HANDBOOK IS STILL IN DRAFT VERSION AND NOT YET AVAILABLE FOR DISTRIBUTION – THIS NOTE IS FOR FACILITATORS REFERENCE ONLY
Outputs are changes in skills or abilities, or the availability of new products and services that must be achieved with the resources provided and within the time-period specified. Outputs are the level of result where the clear comparative advantages of individual agencies emerge and where accountability is clearest.
- Outputs are where the specific comparative advantages of different agencies emerge
- Outputs are not completed activities – they are changes that result from the completion of a set of activities: Policy analysis, Training, Workshops, Surveys – these are activities. The outputs are the new skills, abilities, products or services, that result from a combination of activities.
Indicators are necessary to measure achievement of the outcomes and outputs. More detailed guidance on how to develop outcome and output statements is available in the technical briefs for outcomes and outputs.

## Slide 5
Results Matrix
Notes: 5
Before the training ascertain whether the UNCT has taken a decision on which of option 1A or 1B they will use. If a decision has been taken, show the appropriate version. See note on pros and cons of the different options.
From UNDAF Guidelines, p15-16
Options: UNCTs have two options for the level of results in the UNDAF results matrix The UNCT, with the government, determines which option responds best to the country context. UNCTs have the flexibility to either keep the UNDAF results matrix at the outcome level (Option 1a), or develop a fuller results matrix, that includes outputs (Option 1b). Both options include indicators, baselines, targets, means of verification, risks and assumptions, role of partners and resources. The results chain and accountability system have to be agreed upon by all stakeholders.
UNDAF Option 1A.
If a UNCT chooses Option 1a, it may prepare an UNDAF Action Plan or a similar common operational plan reflecting the outputs that contribute to the outcomes of the UNDAF. The results chain would then be:
Outcomes (UNDAF) ← Outputs & Key Actions (UNDAF Action Plan) ← Activities (Annual Work Plans).
If the UNCT is not preparing an UNDAF Action Plan or a similar common operational plan, then it must ensure the flow of the results chain through:
Outcomes (UNDAF) ← Outputs, Key Actions & Activities (Agency-specific bi-annual and annual work plans; CPAPs; Joint Programmes; Project Documents).
The inter-agency groups responsible for M&E ensure that the output level contributions of all agencies to the outcomes of the UNDAF are captured, monitored and reported on.
Key Benefits:
Strategic focus: By keeping the UNDAF results matrix at the outcome level, the UNCT can present its collective strategic priorities and niche in the country more clearly.
Accountability: With introduction of the UNDAF Progress Report, UNCTs are increasingly being held accountable for their contribution to results at the UNDAF outcome level in addition to outputs, regardless of where they are reflected. A stronger focus on outcomes in the UNDAF supports this shift in accountability.
Concise format: Focus on outcomes facilitates a lean UNDAF results matrix. The UNCT’s strategic priorities, including key indicators, risks and assumptions, role of partners and required resources will be accessible in just a few pages.
Validity: Since outcomes usually do not change, the UNDAF remains valid as the UNCT’s strategy for the entire programming cycle and does not need to be updated annually.
Issues to consider:
No substitute for outputs: The UNCT still has to develop the next level of results, namely outputs, which then need to be specified in an UNDAF Action Plan, agency CPAPs or equivalent.
No substitute for prioritization: A shorter results matrix at outcome level is – by itself – no guarantee for a strategic UNDAF. It is critical that UNCTs rigorously prioritize results at all levels – outcomes, outputs, and activities – and limit outputs and indicators to a manageable number, regardless of whether they are contained in the UNDAF, the UNDAF Action Plan or CPAPs.
Risk of disconnected results chain: It is advisable that UNCTs do not defer the development of outputs to a later stage. A logical and coherent results chain requires that outputs and outcomes are developed simultaneously and in an iterative way: outcomes have to be adjusted in light of outputs and vice versa in order to ensure that outputs contribute logically towards outcomes through a coherent ‘if…then…’ logic.
If the UNDAF remains at the outcome level, outputs can either be defined in an UNDAF Action Plan or in agency documents like CPAPs
Regardless of the option chosen, agencies are accountable for their respective contributions towards the achievement of outcomes. Agencies are fully accountable for their respective outputs. Outputs can be shared by two or more agencies and their implementing partners only if they indicate an opportunity for joint programming. Outputs can be adjusted, where necessary, to take account of changes in the development environment, including changes in availability of resources. (See One Budgetary Framework)
5

## Slide 6
Results Matrix
Notes: 6
HIDDEN SLIDE
From UNDAF Guidelines, p15-16. See note on pros and cons of the different options.
UNDAF Option 1B.
Options: UNCTs have two options for the level of results in the UNDAF results matrix The UNCT, with the government, determines which option responds best to the country context. UNCTs have the flexibility to either keep the UNDAF results matrix at the outcome level (Option 1a), or develop a fuller results matrix, that includes outputs (Option 1b). Both options include indicators, baselines, targets, means of verification, risks and assumptions, role of partners and resources. The results chain and accountability system have to be agreed upon by all stakeholders.
If a UNCT chooses Option 1b, and is not preparing an UNDAF Action Plan or a similar common operational plan, the results chain would then be:
Outcomes & Outputs (UNDAF) ← Outputs & Key Actions (CPAPs/Project documents) ← Activities (Annual Work Plans).
This option represents the conventional format of the UNDAF results matrix.
Key Benefits:
Transparency: Overview of the full extent of UN commitments in the country;
Accountability: A detailed UNDAF results matrix provides the UNCT with a clear accountability framework since the division of labour between agencies only becomes apparent at that level: usually, only one agency is accountable for each output.
Issues to consider:
Transaction costs: Developing a realistic, coherent and logical results framework that includes both outcomes and outputs may be a difficult and time-consuming process. Yet, as experience has shown, this investment in the initial planning stage will greatly facilitate effective implementation, monitoring and evaluation throughout the programming cycle.
Prioritization: Previous UNDAF generations had the tendency to contain far too many outputs and indicators in order to be useful as effective management tools. The UNCT needs to prioritize its results at every level (outcomes, outputs, activities) in line with its capacities and comparative advantage and without compromising the flow of the results chain.
Regardless of the option chosen, agencies are accountable for their respective contributions towards the achievement of outcomes. Agencies are fully accountable for their respective outputs. Outputs can be shared by two or more agencies and their implementing partners only if they indicate an opportunity for joint programming. Outputs can be adjusted, where necessary, to take account of changes in the development environment, including changes in availability of resources. (See One Budgetary Framework)
6

## Slide 7: More specific problems
Tautologies in the results chain
Results not logically linked
Results not sufficiently specific
Results are composites of several results
Results don’t express change (e.g. support provided to strengthen….)
Results statements are too wordy
Confusion between levels of results
Indicators
  Not logically linked to the result
  Not measurable
  Are new results
  Too many!!!
Notes: 7
HIDDEN SLIDE

## Slide 8: Country Examples
Note to facilitation team:
Insert 1-3 slides with results chains from current UNDAF
With their new knowledge, ask participants to reflect on the ‘SMART’ness of their results
Examples from Lao PDR follow…
Notes: 8

## Slide 9: Lao PDR: Current Outcomes
1. By 2011, the livelihoods of poor, vulnerable and food insecure populations are enhanced through sustainable development
2. By 2011, increased and more equitable access to and utilization of quality and prioritized social services
3. By 2011, strengthened capacities of public and private institutions to fulfill their duties and greater people’s participation in governance and advocacy for the promotion of human rights in conformity with the Millennium Declaration.
Notes: HIDDEN SLIDE
These were the current Lao UNDAF Outcomes at the time of the HRBA-RBM workshop.
They are much like the poor examples given earlier. To debrief, no need to say that.
Simply show the group their own current outcomes and ask them to read and offer comments.
Note the comments.
Do not be overly critical. They will be critical of themselves.
Some may point out good aspects of these results. For example, the focus in outcome 1 on vulnerable groups, including food insecure communities.
The overall message here is that, with the application of HRBA, we can do better…
9

## Slide 10
1. By 2011, the livelihoods of poor, vulnerable and food insecure populations are enhanced through sustainable development
1.1 Improved and equitable access to land (between men and women) markets and social and economic services, environmentally sustainable utilization of natural resources, with balanced population growth
Can the UNCT and partners actually do this?
What are the key performance issues or capacity gaps that underlie the situation?
1.2 Increased and more diversified agricultural production, and sustainable use of non-timber forest products
1.3 Improved household food security
1.4 Enhanced ownership and capacity for pro-poor planning and implementation, harmonized aid coordination, and disaster management
1.5 Enabled environment for growth with equity.
For this chain, 43 indicators – none at outcome level
Notes: HIDDEN SLIDE
10

## Slide 11
2. By 2011, increased and more equitable access to and utilization of quality and prioritized social services
2.1 Increased and equitable access to quality basic education;
Tautology
2.2 Improved equity, efficiency and quality of health services with increasing health services coverage with an emphasis on maternal and child health, family planning, nutrition,communicable disease control, and water and sanitation
Indicators do not address all 3 dimensions
2.3 Increased coverage of quality HIV and AIDS prevention, treatment, care and support,focusing on the most vulnerable groups (including children) as defined in the national strategy on HIV and AIDS, sexually transmitted infections.
Ambition?
Notes: HIDDEN SLIDE
11

## Slide 12
3. By 2011, strengthened capacities of public and private institutions to fulfill their duties and greater people’s participation in governance and advocacy for the promotion of human rights in conformity with the Millennium Declaration.
If – then logic…?
3.2 Increased and more equitable access to justice and strengthened rule of law
Are we reaching a bit far?
3.4 Progressive realization of international treaty obligations, including protection of human rights, in accordance with the Lao Constitution and the Millennium Declaration
These sound more like National priorities
Notes: HIDDEN SLIDE
12

## Slide 13: Examples
Papua New Guinea (2008-2012)
Outcome 1.1 National and selected Provincial Parliaments function more effectively and carry out their legislative and oversight roles
  - No. users (MPs, committees, researchers) of services provided by Parliamentary Services (legal, research, library etc.);
  - Quantity and Quality of Legislation prepared and approved.
Outcome 4.3 By 2012, girls will experience fewer inequalities attending school
  - A National plan and budget to implement the girls’ education policy;
  - No. of Child Friendly Schools in programe areas
  - No. of teachers trained to provide counselling;
  - % increase in girls enrolment and retention in programme areas
Notes: HIDDEN SLIDE
Papua New Guinea (2008-2012)
Outcome 1.1 National and selected Provincial Parliaments function more effectively and carry out their legislative and oversight roles
- No. users (MPs, committees, researchers) of services provided by Parliamentary Services (legal, research, library etc.);
- Quantity and Quality of Legislation prepared and approved.
Output 1.1.2 Provincial legislative mechanisms are established and operational in selected Provinces and linked to national parliament systems
Outcome 2.3 By 2012, vulnerable children and youth will experience improved access to quality basic social services, including protection and justice services, particularly in rural and isolated areas
- No. relevance and range of basic services that are accessible to vulnerable children, particularly in rural areas
- No. orphans and vulnerable children accessing health, education, welfare and birth registration services
Outcome 3.1 By 2012, DEC effectively plans, manages, monitors and coordinates with other relevant government institutions the sustainable use of natural resources
- Government has capacity to enforce legislation and policies;
Government has a plan to mainstream environmental issues.
Output 3.1.2 Communities in selected provinces have the capacity to use their natural resources sustainably to enhance their livelihoods.
- Training on more sustainable use of community resources;
- Selected communities have the capacity to access funding and manage small grants projects.
(an activity and a new result – how could we re-position these as indicators?)
Outcome 4.3 By 2012, girls will experience fewer inequalities attending school
- A National plan and budget to implement the girls’ education policy;
- No. of Child Friendly Schools in programe areas
- No. of teachers trained to provide counselling;
- % increase in girls enrolment and retention in programme areas
13

## Slide 14: Examples
Uganda (2010-2014)
Evidence-based policies, strategies and plans are reviewed, developed and adequately resourced through participatory and inclusive approaches to increase access to quality social services.
Azerbaijan (2011-2015)
By 2015, civil society, media, and vulnerable groups enjoy increased roles in policy formulation and implementation processes.
Rwanda (2008-2012)
Capacity of key public and private institutions strengthened to apply gender equality principles and standards in performance, practices and behavior
Vietnam (2006-2010)
Strengthened legislative process, legal safeguards and justice mechanisms for vulnerable groups, ensuring consistency between the legal system and constitutional norms and international treaties
Notes: HIDDEN SLIDE
Use the 4 key HRBA questions on flip chart to get feedback from participants.
Other examples are listed below, including indicators:
Botswana (2010-2016)
Strengthened human rights institutions respond to the rights of vulnerable groups (youth, children, women, people living with HIV and AIDS, refugees and disabled).
Uganda (2010-2014)
Vulnerable populations in Uganda, especially in the north, benefit increasingly from sustainable and quality social services by 2014.
Evidence-based policies, strategies and plans are reviewed, developed and adequately resourced through participatory and inclusive approaches to increase access to quality social services.
Indicators:
A standard set of NDP indicators is agreed on, consolidated and being reported on nation-wide; Baseline: Not in place (2009/2010); Target: In place by 2012
HIV national policy composite index scores; Baseline: 67.5 of 100 points (2005); Target: 85 by 2012
Azerbaijan (2011-2015)
By 2015, civil society, media, and vulnerable groups enjoy increased roles in policy formulation and implementation processes.
Namibia (2006-2010)
By 2010, livelihoods and food security among most vulnerable groups are improved in highly affected locations
Rwanda (2008-2012) Outcome 4: Gender equality
Capacity of key public and private institutions strengthened to apply gender equality principles and standards in performance, practices and behavior
Vietnam (2006-2010) Outcome 4.5
Strengthened legislative process, legal safeguards and justice mechanisms for vulnerable groups, ensuring consistency between the legal system and constitutional norms and international treaties
14

## Slide 15: Refining results…
To strengthen the capacity of health workers to do X by undertaking Y,…
The capacity of health workers is strengthened to do X by undertaking Y,…
The capacity of health workders in the
4 poorest districts is strengthened to
do X by undertaking Y,…
The capacity of health workers in the 4 poorest districts is strengthened to do X
by undertaking Y,…
Health workers in the 4 poorest districts are better able to X
Let’s use results language to emphasis the future condition we want to achieve.
All health workers, everywhere? Can you be more specific? Are there particularly weak or under-resourced health workers we should emphasise?
We can take out information that relates to either strategy or activities.
Now, let’s try bringing the subject of change to the front, and shifting from passive to active language.
Notes: HIDDEN SLIDE
15

## Slide 16: A Human Rights-Based Approach to Monitoring
Notes: 16

## Slide 17: What is Monitoring?
Track progress towards the agreed results in the UNDAF matrix
Checks if assumptions made and risks identified at the design stage are still valid or need to be reviewed
Allows UNCTs and implementing partners to make mid-course corrections as an integral part of programme management
Notes: HIDDEN SLIDE
17

## Slide 18: And Why Do We Need It?
Regular and systematic assessment of progress
Continued review of partners’ capacity development needs
Improve results-based reporting on achievements
Strengthen teamwork and ownership of the UNDAF among implementing partners
Notes: HIDDEN SLIDE
18

## Slide 19: What is Evaluation?
An external function that is separated from programme management
Determines whether results made a worthwhile contribution to national development priorities
3 key questions:
  Did the UNDAF make the best use of the UNCT’s comparative advantages in the country?
  Did the UNDAF generate a coherent UNCT response to national priorities?
  Did the UNDAF help achieve the selected priorities in the national development framework?
Notes: 19
19
HIDDEN SLIDE
RBM in Evaluation
Evaluation is an essential step in the RBM life cycle and a requirement for the UNDAF. The United Nations Evaluation Group (UNEG) standards and norms seek to facilitate system-wide collaboration on evaluation by ensuring that evaluation entities within the UN follow agreed on basic principles.
Box 1 Defining Evaluation: ―An evaluation is an assessment, as systematic and impartial as possible, of an activity, project, programme, strategy, policy, topic, theme, sector, operational area, institutional performance, etc. It focuses on expected and achieved accomplishments, examining the results chain, processes, contextual factors of causality, in order to understand achievements or the lack thereof. It aims at determining the relevance, impact, effectiveness and sustainability of the interventions and contributions of the organizations of the UN system.‖ An evaluation should provide evidence-based information that is credible, reliable and useful, enabling the timely incorporation of findings, recommendations and lessons into the decision-making processes of the organizations of the UN system and its members.
(UNEG Norms for Evaluation in the UN System, 2005: 5)
It is important to distinguish the role of evaluation in RBM in the following two aspects:
Role of evaluation as a critical management tool for achieving better results; and
Role of the evaluation function in RBM processes (quality assurance).
Evaluation has three key functions:
(1) Utilization. As an input to provide decision-makers with knowledge and evidence about performance and good practices;
(2) Accountability. To donors, funders, political authorities, stakeholders and the general public, and
(3) Contribution. To institutional policy-making, development effectiveness and organizational effectiveness.

## Slide 20: And why do we need to do it?
Whether we are Doing the Right Things
  Relevance/rationale/justification
  Client satisfaction
Whether we are Doing it Right
  Effectiveness/coherence
  Efficiency: optimizing resources
  Sustainability
  Impact
Whether there are Better Ways of Doing it
  Alternatives
  Good practices
  Lessons learned
  Improved positioning to influence next development planning framework
Notes: HIDDEN SLIDE
RBM Handbook, p.30-31 THIS HANDBOOK IS STILL IN DRAFT VERSION AND NOT YET AVAILABLE FOR DISTRIBUTION – THIS NOTE IS FOR FACILITATORS REFERENCE ONLY
Evaluation as a critical management tool for achieving better results –Utilization
Evaluations help to improve development effectiveness and provide critical inputs for managing for results. Through the generation of ‗evidence‘ and objective information, evaluations enable managers to make informed decisions and plan strategically. Ability of organizations to carry out credible evaluations and use them to make evidenced based decisions is critical. The focus is on what works, why and in what context. Decision makers, such as managers, use evaluations to make the necessary improvements, adjustments to the implementation approach or strategies and to decide on alternatives.
Evaluation function in RBM processes (Quality Assurance) for Accountability
This determines the merit or worth and value of an initiative/programme and its quality. An effective accountability framework requires credible and objective information, and evaluations can deliver such information. Over time, the accountability function has expanded from primarily donors and government to stakeholders and beneficiaries of development interventions. By providing objective and independent assessments, evaluations support the organisation‘s accountability towards its governing board, donors, governments, national partners and beneficiaries.
Evaluation for building knowledge for wider application –Contribution & Learning
When the interest is in the development of knowledge for global use and for generalization to other contexts and situations, evaluations generally apply more rigorous methodology to ensure a higher level of accuracy in the evaluation and the information being produced to allow for generalizability and wider application beyond a particular context. Evaluations should not be seen as an event but as part of an exercise whereby different stakeholders area able to participate in the continuous process of generating and applying evaluative knowledge. An evaluation framework that generates knowledge, promotes learning and guides action is an important means of capacity development and sustainability of results.
20

## Slide 21: Experience from the Field
UNDAF Monitoring is NOT OPERATIONAL
UNDAF Outcome groups not formed or meet rarely
Responsibilities not in performance appraisal instruments
Group members not rewarded for their UNDAF monitoring efforts
UNDAF Outcome groups become paper entities
Most importantly…
No regular or coherent reporting to the UNCT about overall progress towards UNDAF results
Notes: HIDDEN SLIDE
Combined UNDAF and agency monitoring & reporting requirements overwhelm UN capacities at country level
21

## Slide 22: Response from UNDG
Simplified M&E process
M&E Plan
Annual Review Process
Single Progress Report per UNDAF cycle
Evaluation
What changed?
No more Annual Reporting to UNDG required
M&E matrix merged with UNDAF Results Matrix
Notes: HIDDEN SLIDE
22

## Slide 23: M&E Plan
Designed at same time as the UNDAF Results Matrix
Highlights mechanisms or modalities for monitoring the achievement of outputs and contributions towards outcomes
Key considerations
Indicators for UNDAF results to be drawn from national systems
If data not available, baseline studies can be supported
The M&E Plan may be reflected in a table or in the narrative of the UNDAF document
Notes: HIDDEN SLIDE
23

## Slide 24: UNDAF outcome groups:
UNDAF outcome/ thematic groups are expected to:
  Meet regularly with partners to assess progress;
  Conduct joint monitoring missions (as appropriate)
  Report regularly to the UNCT on the above, and assist the UNCT to bring lessons and good practices to the attention of policy makers
  Conduct and document annual progress reviews of the UNDAF (on basis of M&E plan)
The UNCT should…
  Recognise their responsibilities group members in performance appraisal instruments
  Ensure that UNDAF groups have resources and secretariat support to function
Notes: HIDDEN SLIDE
RBM Handbook, p.28-29 THIS HANDBOOK IS STILL IN DRAFT VERSION AND NOT YET AVAILABLE FOR DISTRIBUTION – THIS NOTE IS FOR FACILITATORS REFERENCE ONLY
Monitoring and Evaluation of the UNDAF as a System
UNCTs need to ensure that an effective M&E system is in place to monitor and evaluate its work prior to the implementation of programmatic work under UNDAF. In practice monitoring has to be considered and initially planned in the planning and analysis stages when key issues such as data, national M&E capacities and stakeholder needs and engagement are first encountered. It is always easier to develop such initial M&E plans at the beginning in the UNDAF process and then gradually strengthen them as the UNCT members move on to implementation stages.
Functioning inter-agency outcome or thematic M&E groups linked to national M&E mechanisms– for example, sector-wide coordinating mechanisms – are most important to ensure that UN system‘s monitoring is effective and relevant nationally25. Partnerships within UN systems and with external partners are key to outcome monitoring. UN inter-agency groups coordinating at the outcome level are expected to monitor and report regularly to the UNCT on outcome-level performance. As mentioned earlier, this reporting should to the extent be feasible based on the UNCT‘s credible engagement in, and use of, national monitoring mechanisms. A number of tasks fall under the purview of this inter-agency outcome/M&E group:
- Meet regularly with partners to assess progress;
- Conduct coordinated joint monitoring missions as appropriate;
- Report regularly to the UNCT on the above and assist the UNCT to bring objective monitoring evidence, lessons learned and good practices to the attention of policy-makers;
Conduct and document annual progress reviews of the UNDAF, using the M&E plan as a framework.
The UNCT can itself support group members in fulfilling these roles by:
1. Recognizing their inter-agency responsibilities in assessing performance at the outcome level;
2. Ensuring that UNDAF M&E groups have resources and secretariat support.
24

## Slide 25: Key Elements of Simplified M&E Process
Evaluation
Annual Review Process
Reporting
Align the UNDAF annual review process with the national review process.
To facilitate this, interagency groups are formed around each national priority
UNDAF evaluation is REQUIRED.
It is linked with national evaluations. However, the modalities are flexible.
Annual reporting is NOT required.
A single UNDAF progress report is required per UNDAF cycle.
Notes: HIDDEN SLIDE

## Slide 26: Assumptions & Risks
Notes: 26
  HIDDEN SLIDE

## Slide 27: Assumption: A Definition
A necessary condition for the achievement of results at different levels
Part of the cause-effect logic
Stated as though it is actually the case
Often very un-predictable at higher levels
Can help identify additional results or outputs
Notes: 27
HIDDEN SLIDE

## Slide 28: Risk: A Definition
A potential event or occurrence beyond the control of the programme that could adversely affect the achievement of the desired results
   A threat to success
Not just the negative of an assumption
A trigger for reconsideration of strategic direction
Notes: 28
HIDDEN SLIDE

## Slide 29: Assumptions & Risks
Prov. Govt disburses its planned financial support for the micro-credit initiatives
Indigenous communities in Belem Province enjoy a higher standard of living
Indigenous families involved in micro-credit initiatives have increased employment and incomes
Risk: Return of hyper-inflation
Income generating micro-credit initiatives are implemented
if
and assuming…
if
and assuming…
Local market demand for the products generated
Families use their new incomes to meet basic needs (pay school fees, etc.)
then
then
Notes: 29
HIDDEN SLIDE
Debriefing
- Reveal Assumptions #1 and #2 between the output and outcome, and ask the participants for their opinions
- Assumption #1 is not a good one. Why? The condition being assumed (“that the market for products already exists”) is a fatal one – ie. it is absolutely essential for the sustainability of the programme, and should have been assessed before the programme started.
- Ask participants, “What could be done to address this situation during the programme design phase?” OR “What should the programme staff do to address this possible fatal assumption?”
A good answer is “Conduct market surveys during the planning phase to assess demand for the anticipated products and services generated by the micro-projects”
A key point here is that assumptions help to reveal gaps in our logic of results – by adding additional results, we can make a programme design less risky
- Assumption #2 is a relatively good one. The key word in the assumption is “planned” – ie. government is committed to disburse the financial credits. It can be verified with partners or in planning documents. But it still remains outside the control of the programme and so needs an assumption.
- Reveal Assumption #3 between the outcome and impact, and again ask for feedback.
- It could be good or bad depending on the perceptions of participants. There is no clear right answer in this example
- On one hand, this condition about the use of revenue at family level could be addressed by including other behavioural change outcomes related to family knowledge about the need to spend scarce resources on basic needs like school fees. It would also be possible to target women’s associations and cooperatives specifically for the preferential credits
- On the other hand, no amount of awareness-raising can fully control individual behaviours – there has to be a level of trust that families will do the right thing, and so the assumption is a necessary one.

## Slide 30
Results Matrix
Notes: 30
HIDDEN SLIDE
Option 1A. This and the next slide describe visually the differences in the Results Matrix described in slide 20.
30

## Slide 31
Results Matrix
Notes: 31
HIDDEN SLIDE
Option 1 B. This and the last slide describe visually the differences in the Results Matrix described in slide 20.
31

## Slide 32: Group Work
In Groups…
Develop 1 key assumption between an outcome and its contributing outputs
Identify 1 critical risk for the results framework overall…and add to your results framework
Risk
Assumption
Notes: 32
HIDDEN SLIDE